## Tasks
Status | Value Table | 1 |  | 0.75 |  | 0.5
Not Started | Type | Type Weight | Urgency | Urgency Weight | Personal Interest | Interest Weight
Research | Concept | 1 | Urgent | 0.75 | Javascript/HTML | 0.5
Development | Core Enhancement | 0.8 | Not Urgent | 0.5 | Python | 0.33333
Waiting | Integration | 0.6 | Nice To Have | 0.25 | Organization | 0.16667
Testing | Bug | 0.4 |  | 0 |  | 0
Complete | Cosmetic Enhancement | 0.2 |  | 0 |  | 0
Task Table
| Type | Urgency | Personal Interest | Weight | Task | Status | Notes
| Concept | Urgent | Organization | 63.89% | Class Structure/Data Layout | Complete
| Concept | Not Urgent | Organization | 55.56% | App Basic Visual Layout / Inputs List | Complete
| Core Enhancement | Urgent | Javascript/HTML | 68.33% | Save table changes in database | Not Started
| Cosmetic Enhancement | Not Urgent | Javascript/HTML | 40% | React Reasearch | Complete | Decided to stick with vallinalla JS
| Core Enhancement | Not Urgent | Javascript/HTML | 60% | Write Calculations from JS | Not Started
| Core Enhancement | Not Urgent | Javascript/HTML | 60% | "Add" Button | Not Started
| Core Enhancement | Not Urgent | Javascript/HTML | 60% | "Delete" Button | Not Started
| Core Enhancement | Not Urgent | Javascript/HTML | 60% | Drag Tables | Not Started
| Core Enhancement | Not Urgent | Javascript/HTML | 60% | Add a category weighting | Not Started
| Concept | Not Urgent | Organization | 55.56% | Maintenance Access concept | Not Started
| Integration | Not Urgent | Python | 47.78% | Email integration | Not Started
| Bug | Nice To Have | Javascript/HTML | 38.33% | Fix JS for laterally dragging of tables | Not Started
| Cosmetic Enhancement | Nice To Have | Javascript/HTML | 31.67% | Make a "Wait" option for tasks | Not Started
| Cosmetic Enhancement | Nice To Have | Javascript/HTML | 31.67% | Attacht File option for Tasks | Not Started
| Cosmetic Enhancement | Nice To Have | Javascript/HTML | 31.67% | Timer For Breaks | Not Started
| Cosmetic Enhancement | Nice To Have | Javascript/HTML | 31.67% | Social Page for Organizational Ideas (videos, articles) | Not Started
| Cosmetic Enhancement | Nice To Have | Javascript/HTML | 31.67% | reminder every hour about what just happened | Not Started
Note on A1: Beau Batchelor: Do Not Touch
Note on D1: Beau Batchelor: Category Weighting
Note on F1: Beau Batchelor: Category Weighting
Note on H1: Beau Batchelor: Category Weighting